## WBS
Work Breakdown Structure |  |  |  | Developed by Analysistabs®
| Project ID 4 | P#1001 |  | Start Date 4 | 2024-06-18 | Project Objective 6
| Project Name 4 | NextGen Software Rollout |  | End Date 4 | 2024-06-18 | To deploy a new software system that improves data processing efficiency and user interface across all departments within the organization.
| Project Manager 4 | Alice Johnson |  | Created On 4 | 2024-06-18
| Project Sponsor 4 | XYZ Corporation’s IT Department |  | Last Updated 4 | 2024-06-18
Work Breakdown Structure (WBS)
WBS ID | Task | Responsible | Dependencies | Start | Finish | Cost | Remarks
1 | Project Initialization | Alice | None | 2024-01-01 | 2024-01-07 | 1000 | Kick-off meeting
1.1 | Requirement Analysis | Bob | 1 | 2024-01-08 | 2024-01-15 | 2000 | Gathering requirements
1.2 | Project Plan Development | Charlie | 1.1 | 2024-01-16 | 2024-01-23 | 1500 | Drafting project plan
2 | Design Phase | Dana | 1.2 | 2024-01-24 | 2024-02-14 | 4000 | High-level design
2.1 | Architecture Design | Eve | 2 | 2024-02-15 | 2024-02-28 | 3000 | System architecture
2.2 | Detailed Design | Frank | 2.1 | 2024-03-01 | 2024-03-15 | 2500 | Component design
3 | Development Phase | George | 2.2 | 2024-03-16 | 2024-05-01 | 10000 | Coding tasks
3.1 | Backend Development | Hilda | 3 | 2024-05-02 | 2024-06-15 | 5000 | Database setup
3.2 | Frontend Development | Ian | 3 | 2024-06-16 | 2024-07-30 | 4500 | User interface
4 | Testing Phase | Jane | 3.1, 3.2 | 2024-08-01 | 2024-09-01 | 5000 | System testing
4.1 | Integration Testing | Kyle | 4 | 2024-09-02 | 2024-09-15 | 2000 | Link systems
4.2 | User Acceptance Testing | Laura | 4.1 | 2024-09-16 | 2024-10-07 | 1500 | Final verification
5 | Deployment Phase | Mike | 4.2 | 2024-10-08 | 2024-10-22 | 3000 | Go-live preparation
5.1 | Production Setup | Nina | 5 | 2024-10-23 | 2024-11-05 | 2500 | Setup production env
5.2 | Launch | Oscar | 5.1 | 2024-11-06 | 2024-11-10 | 1000 | Official launch
6 | Post-Launch Support | Patricia | 5.2 | 2024-11-11 | 2024-12-31 | 3000 | Support and updates
6.1 | Customer Feedback Collection | Quinn | 6 | 2025-01-01 | 2025-02-01 | 1200 | Collect feedback
6.2 | Issue Resolution | Rachel | 6.1 | 2025-02-02 | 2025-03-15 | 2000 | Fixing reported issues
6.3 | Project Closure | Steve | 6.2 | 2025-03-16 | 2025-03-31 | 500 | Documenting the project
6.4 | Review Meeting | Tina | 6.3 | 2025-04-01 | 2025-04-15 | 300 | Project review
i This is a free template by Projectmanagementtemplate.net Powered By Analysistabs ™, you can use this template to create simple Project Charters, check our premium templates for editable/unlocked versions and more verity of templates.
4 View Details

## Intro
| Excel Work Breakdown Structure Template | Get our Premium Project Management Templates
Free Excel Template by analysistabs.com
Info 4 | Free Work Breakdown Template for Excel: Break down your project into smaller, more manageable tasks.
Usage 4 | Go to 'Template' sheet, enter the define your project details and WBS items in the dedicated sections of the template. Plan your project roadmap with well developed WBS Template.
Share 4 | Projectmanagementtemplate.net powered by Analysistabs ™ is developing Free and Premium l Project Management Templates. Please do not share this downloaded file. Instead, you can share our free template page link with your colleagues and friends, it helps us to create better tools and more templates.
Email 4 | Please share your feedback or ask questions, Email: info@analysistabs.com
Please Visit us
Visit us for more Free Templates and Premium Templates |  |  | Progress | 2501 days | TOTAL TASKS 4 | 1
|  |  | #REF! | 0 | Completed | #REF!
|  |  | #REF! | 2500 | In progress | #REF!
|  |  |  | #NAME? | Not Started | #REF!
i Please do not delete this worksheet. Instead, you can hide the sheet.
4 Download Now
*
1

## License
License Terms
4 | Analysistabs™ License Agreement
This Template/Excel File and sample data is created by Analysistabs™
4 | Single User License: Allows 1 (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this template for their personal use only
4 | You can share the template page link:(https://analysistabs.com/project/management/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
Link: | https://analysistabs.com/project/management/
Hello! it’s a sheet
Calculations ->
|  | Progress | 2501 days | 0 | TOTAL TASKS 4 | 1
|  | #REF! | 0 | 0 | Completed | #REF!
|  | #REF! | 2500 | 0 | In progress | #REF!
|  | 0 | #NAME? | 0 | Not Started | #REF!